## Projects_Export_Sheet
PROJECT ID | PROJECT NAME | PERCENTAGE COMPLETED | OWNER | STATUS | OPEN TASKS | CLOSED TASKS | OPEN MILESTONES | CLOSED MILESTONES | OPEN ISSUES | CLOSED ISSUES | START DATE | END DATE | PLANNED COST | ACTUAL COST | BUDGET BALANCE | PLANNED HOURS | ACTUAL HOURS | HOURS REMAINING | COST BUDGET | BUDGET TYPE | BILLING METHOD | FORECASTED HOURS | FORECASTED COST | TAGS | PLANNED COST (USD) | ACTUAL COST (USD) | FORECASTED COST (USD) | PLANNED VALUE | EARNED VALUE | SCHEDULE VARIANCE | COST VARIANCE | PLANNED VALUE (USD) | EARNED VALUE (USD) | SCHEDULE VARIANCE (USD) | COST VARIANCE (USD) | BUDGETED HOURS | LOCATION | CONSORTIUM | PROJECT CODE | BUSINESS UNIT | OPPORTUNITY ID
MA-215 | NCR BEYON - Data Governance Framework – Phase 1 | 11% | Jessica Aoun | Active | 61 | 8 | 7 | 1 | 0 | 0 | 09-01-2025 | 01-31-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-214 | ADPG - Staff Augmentation | 0% | Lina Gharzeddine | Active | 27 | 0 | 5 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-213 | ADPG - mPulse Milahi Chatbot | 0% | Lina Gharzeddine | Active | 8 | 0 | 10 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-212 | NDI Assessment Platform | 0% | Karim Fleifel | In Progress | 38 | 0 | 3 | 0 | 0 | 0 | 07-29-2025 | 07-29-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | - | Internal MAT | -
MA-211 | BBAC- Informatica PWC Health Check & Upgrade | 9% | Jessica Aoun | Active | 66 | 7 | 1 | 1 | 0 | 0 | 07-10-2025 | 09-30-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-210 | SAIB - Data Management Office | 0% | Amr Waly | Active | 19 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR000000 | Maaloomatiia | OPP-
MA-209 | M-AGNT.AI | 9% | Stefano El- Khoury | Active | 241 | 29 | 7 | 0 | 24 | 0 | 06-19-2025 | 06-19-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | - | - | -
MA-208 | POC FTA - eInvoicing CDP | 100% | Rakesh Rathod | In Progress | 0 | 26 | 0 | 0 | 0 | 0 | 06-09-2025 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dubai | - | PR000000 | Maaloomatiia | OPP-
MA-207 | GDRFAD - Unstructured Violation Reports (LLM UC) | 57% | Lina Gharzeddine | Active | 27 | 37 | 5 | 0 | 2 | 3 | 05-28-2025 | 10-23-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000562 | Maaloomatiia | OPP-
MA-206 | Dubai Municipality- Support Project | 14% | Hussein Hammoud | In Progress | 12 | 2 | 0 | 0 | 0 | 0 | 05-15-2025 | 05-14-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000572 | Maaloomatiia | OPP-
MA-205 | SIMAH - MDM | 2% | Rakesh Rathod | In Progress | 719 | 21 | 0 | 0 | 0 | 0 | 06-02-2025 | 09-30-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000063 | Maaloomatiia | OPP-
MA-204 | BAJ - Anti-Fraud Analytics | 34% | Jessica Aoun | Active | 40 | 21 | 0 | 0 | 0 | 0 | 05-04-2025 | 09-30-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000 | Maaloomatiia | OPP-
MA-203 | Alinma - Data Governance | 64% | Jessica Aoun | Active | 12 | 22 | 1 | 5 | 0 | 0 | 12-03-2024 | 05-31-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR00000031 | Maaloomatiia | OPP-
MA-202 | FAHR - Alteryx Implementation | 46% | Rakesh Rathod | In Progress | 23 | 20 | 0 | 0 | 0 | 0 | 03-03-2025 | 03-03-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE - Dubai | - | PR00000515 | Maaloomatiia | OPP-
MA-201 | STC Services- DKU Installation and Self Services | 37% | Hussein Hammoud | In Progress | 15 | 9 | 0 | 0 | 0 | 0 | 01-01-2025 | 08-31-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA- Riyadh | - | PR00000052 & PR00000045 | Maaloomatiia | OPP-349951
MA-200 | OO- Staff Augmentation | 100% | Hussein Hammoud | Completed | 0 | 2 | 0 | 1 | 0 | 0 | 01-01-2025 | 08-14-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000084 | Maaloomatiia | OPP-
MA-199 | QCB Qatar Central Bank | 100% | Stefano El- Khoury | Active | 0 | 1 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000494 | Maaloomatiia | OPP-
MA-198 | OO_ABC- ISM | 47% | Hussein Hammoud | In Progress | 10 | 9 | 0 | 0 | 0 | 0 | 09-26-2024 | 09-25-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000492 | Maaloomatiia | OPP-
MA-197 | EPG - Data Governance | 99% | Jessica Aoun | In Progress | 2 | 300 | 0 | 4 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000493 | Maaloomatiia | OPP-
MA-192 | MIDIS Local Office | 0% | Khaled Mostafa | Active | 2 | 0 | 0 | 0 | 0 | 0 | 10-10-2024 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-191 | EMB - RPA | 0% | Sagar Petluri | Active | 3 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-190 | Saudi Payments | 0% | Sagar Petluri | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-189 | MOCulture - CV Platform Managment | 79% | Jessica Aoun | In Progress | 16 | 65 | 3 | 4 | 1 | 0 | 10-09-2024 | 03-09-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000035 | Maaloomatiia | OPP-
MA-188 | Demo Project | 0% | Stefano El- Khoury | Active | 3 | 0 | 0 | 0 | 0 | 0 | 10-01-2024 | 06-30-2025 | AED 0.00 | AED 200.00 | AED -200.00 | 245:42 | 10:00 | 235:42 | AED 0.00 | Based on User | Based on Staff Hours | 255:42 | AED 200.00 |  | $ 0.00 | $ 734.50 | $ 734.50 | - | - | - | AED -200.00 | - | - | - | $ -734.50 | 0:00 | - | - | PR000000 | Internal MAT | OPP-
MA-187 | OO- Informatica EDC & AXON Setup | 100% | Hussein Hammoud | Completed | 0 | 52 | 4 | 0 | 0 | 0 | 08-15-2024 | 09-30-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR000000 | Maaloomatiia | OPP-1225786
MA-186 | BSF- RPA | 0% | Khaled Mostafa | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-185 | Al Ansari - ECM | 0% | Khaled Mostafa | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-184 | DDA T&M | 0% | Akshara Mannapra | Active | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-183 | TAMM - RPA | 50% | Khaled Mostafa | Active | 1 | 1 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-181 | SAIB -Big data Platform | 81% | Amr Waly | In Progress | 47 | 210 | 15 | 1 | 3 | 13 | 05-01-2024 | 12-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000024 | Maaloomatiia | OPP-
MA-180 | Intelligent Automation Team (Internal) | 83% | Khaled Mostafa | Active | 1 | 5 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-179 | MoHAP CRM Integration | 0% | Akshara Mannapra | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-178 | CBD: ITSM Service Now Integration | 0% | Akshara Mannapra | Active | 3 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-177 | ADNOC - RPA | 10% | Khaled Mostafa | Active | 9 | 1 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-176 | ARO Drilling - RPA | 18% | Khaled Mostafa | Active | 27 | 6 | 0 | 0 | 0 | 0 | 07-01-2024 | 09-30-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA | RPA, AA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA (Remotely) | - | PR000000 | RPA | OPP-
MA-175 | RPA - Presales | 80% | Khaled Mostafa | Active | 1 | 4 | 0 | 0 | 0 | 0 | 01-01-2020 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE, Dubai | - | PR000000 | RPA | OPP-
MA-174 | ENOC - ECM | 62% | Khaled Mostafa | Active | 6 | 10 | 0 | 0 | 0 | 0 | 02-21-2024 | 02-28-2025 | $ 0.00 | $ 0.00 | $ 0.00 | 13:30 | 92:30 | -79:00 | $ 0.00 | Based on User | Based on Staff Hours | 95:29 | $ 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE, Dubai | SER Group | PR00000442 | RPA | OPP-
MA-173 | Mashreq - PS Man-days Engagement - CMDB | 0% | Sagar Petluri | Active | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-172 | DCT | 66% | Sagar Petluri | Active | 4 | 7 | 0 | 0 | 0 | 1 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-171 | SEHA | 0% | Sagar Petluri | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-170 | OO- Data Science_Staff Augmentation | 100% | Hussein Hammoud | Completed | 0 | 20 | 0 | 0 | 0 | 0 | 05-14-2024 | 12-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman - Muscat | - | PR00000072 | Maaloomatiia | OPP-334745
MA-169 | BAJ Change Request - iAgent to CRM | 0% | Sagar Petluri | Active | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-168 | HBTF BHOM Project | 0% | Sagar Petluri | Active | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-167 | FTA ITSM Enhancement | 0% | Sagar Petluri | Active | 5 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA | ITSM, DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-166 | MSS (previously LAD) | 0% | Sagar Petluri | Completed | 4 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-165 | Riyad Bank | 0% | Akshara Mannapra | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-
MA-164 | PCS | 0% | Akshara Mannapra | Active | 3 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-163 | Mashreq | 11% | Sagar Petluri | Active | 8 | 1 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | RPA | OPP-
MA-162 | SAIB - Big Data Platform - Archived | 1% | Mohamed Awad | Completed | 103 | 2 | 0 | 0 | 2 | 0 | 05-01-2024 | 08-31-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 24587:00 | 535:30 | 24051:30 | AED 0.00 | Based on Milestone | Based on Staff Hours | 25023:30 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | KSA | - | PR00000024 | Maaloomatiia | OPP-
MA-161 | DDA | 98% | Rakesh Rathod | In Progress | 3 | 171 | 0 | 0 | 0 | 11 | 05-03-2024 | 01-31-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 6306:20 | 2804:15 | 3502:05 | AED 0.00 | Based on Milestone | Based on Staff Hours | 3516:13 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | - | - | PR00000524 | Maaloomatiia | OPP-
MA-160 | MAF - Informatica Migration | 100% | Jessica Aoun | Completed | 0 | 125 | 0 | 3 | 0 | 0 | 05-06-2024 | 11-22-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | PR00000413 | Maaloomatiia | OPP-
MA-159 | NCR-Batelco - Informatica PowerCenter Upgrade | 100% | Jessica Aoun | Completed | 0 | 5 | 0 | 4 | 0 | 0 | 04-03-2024 | 06-10-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 936:00 | 245:20 | 690:40 | AED 124,865.00 | Based on Milestone | Based on Staff Hours | 245:20 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | Bahrain | - | PR00000068 | Maaloomatiia | OPP-
MA-158 | SIMAH - Informatica Operational Support | 23% | Rakesh Rathod | In Progress | 36 | 11 | 3 | 1 | 0 | 0 | 04-01-2024 | 03-31-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 36729:00 | 2312:00 | 34417:00 | AED 538,633.20 | Based on Milestone | Based on Staff Hours | 29438:00 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | KSA | - | PR00000064 | Maaloomatiia | OPP-
MA-157 | MOHRE - Professional Services | 0% | Rakesh Rathod | In Progress | 6 | 0 | 0 | 0 | 0 | 0 | - | - | AED 0.00 | AED 0.00 | AED 0.00 | 0:00 | 132:35 | -132:35 | AED 0.00 | Based on Milestone | Based on Staff Hours | 132:35 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR000000 | Maaloomatiia | OPP-
MA-156 | SASO - Data Governance | 100% | Jessica Aoun | Completed | 0 | 451 | 0 | 6 | 0 | 0 | 02-05-2024 | 07-31-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 155251:57 | 7853:39 | 147398:18 | AED 0.00 | Based on Milestone | Based on Staff Hours | 7853:39 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | - | - | PR00000019 | Maaloomatiia | OPP-
MA-155 | RTA - MicroStrategy Upgrade | 100% | Jessica Aoun | Completed | 0 | 1 | 0 | 1 | 0 | 0 | - | - | AED 0.00 | AED 0.00 | AED 0.00 | 279:00 | 01:30 | 277:30 | AED 25,500.00 | Based on Milestone | Based on Staff Hours | 01:30 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR00000340 | Maaloomatiia | OPP-466016
MA-154 | SIMAH - Informatica Services | 0% | Rakesh Rathod | In Progress | 5 | 0 | 1 | 1 | 0 | 0 | - | - | AED 0.00 | AED 0.00 | AED 0.00 | 1269:00 | 3028:22 | -1759:22 | AED 159,940.42 | Based on Milestone | Based on Staff Hours | 4297:22 | AED 0.00 | Staff Augmentation | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | KSA | - | PR00000064 | Maaloomatiia | OPP-
MA-153 | KAFD - SoftwareAG Professional Services | 0% | Hussein Hammoud | Completed | 1 | 0 | 4 | 2 | 0 | 0 | - | - | AED 0.00 | AED 0.00 | AED 0.00 | 238:00 | 36:00 | 202:00 | AED 768,866.00 | Based on Milestone | Based on Staff Hours | 107:24 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | KSA | - | PR00000015 | Maaloomatiia | OPP-
MA-152 | RTA - EAIP - Operations, maintenance, and support | 90% | Jessica Aoun | In Progress | 1 | 10 | 1 | 10 | 0 | 0 | 10-25-2023 | 11-09-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 10044:00 | 2629:02 | 7414:58 | AED 3,992,466.59 | Based on Milestone | Based on Staff Hours | 3419:32 | AED 0.00 | Staff Augmentation | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR00000069 | Maaloomatiia | OPP-518693
MA-151 | PMO Internal Project | 10% | Stefano El- Khoury | Junk - Internal | 18 | 2 | 0 | 0 | 0 | 0 | 02-01-2024 | 04-30-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-149 | FHO - FHRP | 93% | Rakesh Rathod | In Progress | 2 | 91 | 9 | 3 | 7 | 29 | 01-29-2024 | 12-31-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 43576:26 | 1959:48 | 41616:38 | AED 4,698,000.00 | Based on Milestone | Based on Staff Hours | 25928:36 | AED 0.00 | DMA | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE - Abu Dhabi | - | PR00000428 | Maaloomatiia | -
MA-147 | TVTC BI Solution | 16% | Rakesh Rathod | In Progress | 58 | 12 | 4 | 1 | 2 | 0 | 03-01-2024 | 09-30-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000034 | Maaloomatiia | OPP-
MA-146 | GDRFA - Dataiku AI Platform | 72% | Mohamed Awad | In Progress | 38 | 108 | 5 | 1 | 11 | 18 | 12-19-2023 | 10-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | PR00000408 | Maaloomatiia | OPP-42300769
MA-145 | DEWA-MORO: BMC Helix implementation & Migration | 9% | Sagar Petluri | Active | 67 | 7 | 6 | 0 | 0 | 0 | 12-05-2023 | 09-01-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | MORO, DEWA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | ITSM | OPP-311779
MA-144 | Network International | 0% | Akshara Mannapra | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-143 | Support cases | 0% | Akshara Mannapra | Active | 9 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-142 | BA Activities Tracker | 0% | Maria Rizk | Active | 2 | 0 | 1 | 0 | 0 | 0 | 11-10-2023 | 12-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Internal MAT | OPP-
MA-141 | MOC - Data Governance Implementation | 100% | Jessica Aoun | Completed | 0 | 29 | 0 | 9 | 0 | 0 | 10-02-2023 | 08-01-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR00000416 | Maaloomatiia | OPP-
MA-140 | OO- CR6 | 94% | Hussein Hammoud | Completed | 1 | 17 | 4 | 2 | 0 | 0 | 10-16-2023 | 03-29-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000003 | Maaloomatiia | OPP-
MA-139 | DET - Data Analytics & Modeling | 96% | Karim Fleifel | Completed | 0 | 79 | 0 | 6 | 3 | 13 | 01-29-2024 | 09-06-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000433 | Maaloomatiia | OPP-
MA-138 | BAJ - Data Platform Modernization | 97% | Mohammed Albarrak | In Progress | 14 | 445 | 12 | 10 | 0 | 48 | 09-17-2023 | 03-10-2025 | AED 0.00 | AED 0.00 | AED 0.00 | 18221:07 | 7192:02 | 11029:05 | AED 6,551,414.00 | Based on Milestone | Based on Project Hours | 20836:02 | AED 0.00 |  | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | - | - | PR00000404 | Maaloomatiia | OPP-
MA-137 | FAHR - DMA - DWH Enhancement | 32% | Rakesh Rathod | In Progress | 297 | 142 | 9 | 2 | 0 | 0 | 09-01-2023 | 12-31-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 1069617:00 | 12815:00 | 1056802:00 | AED 1,227,500.00 | Based on Milestone | Based on Staff Hours | 918255:30 | AED 0.00 | Staff Augmentation | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR00000396 | Maaloomatiia | OPP-538421
MA-135 | AD Police - PowerCenter Support | 0% | Dalia El Hajj | Completed | 1 | 0 | 0 | 0 | 0 | 0 | 04-01-2023 | 03-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-134 | POC - DEWA | 0% | Rohit Bhattacharjee | Cancelled | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR000000 | Maaloomatiia | OPP-
MA-132 | KAFD - DMA: Data Management Professional Services | 76% | Hussein Hammoud | In Progress | 63 | 201 | 6 | 0 | 0 | 0 | 07-24-2023 | 07-20-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000008 | Maaloomatiia | OPP-507050
MA-131 | OO - Advanced Analytics Use Case Implementation | 100% | Hussein Hammoud | Completed | 0 | 12 | 3 | 5 | 0 | 0 | 02-01-2024 | 06-28-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000055 | Maaloomatiia | OPP-506991
MA-130 | MAF - DataRobot Fashion | 21% | Karim Fleifel | Completed | 97 | 26 | 2 | 3 | 3 | 2 | 07-15-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | PR00000413 | Maaloomatiia | -
MA-128 | DAMAC: BMC Helix ITSM | 3% | Akshara Mannapra | Active | 86 | 3 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | ITSM | -
MA-127 | AUB - Security Incident Management | 25% | Waseem Zawaideh | Active | 3 | 1 | 0 | 0 | 0 | 0 | 07-26-2023 | 10-13-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | ITSM | -
MA-126 | MAG - Quality Assurance Framework | 0% | Stefano El- Khoury | Active | 2 | 0 | 0 | 0 | 0 | 0 | 07-24-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA to NA; NA to -
MA-125 | MAG - Project & Timesheet Governance | 0% | Stefano El- Khoury | Active | 11 | 0 | 1 | 0 | 1 | 0 | 07-24-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA to NA; NA to -
MA-124 | MAG - Document & Content Management | 0% | Stefano El- Khoury | Active | 1 | 0 | 0 | 0 | 0 | 0 | 07-24-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA to NA; NA to -
MA-123 | NCR-Batelco - DMA - Data Governance PH2 | 100% | Jessica Aoun | Completed | 0 | 43 | 0 | 7 | 0 | 1 | 06-20-2023 | 05-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | Batelco - NCR | PR00000056 | Maaloomatiia | OPP-507286
MA-122 | FAB - Contrl-M Training | 0% | Waseem Zawaideh | Active | 1 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | [17 empty] | 202111_UAE_001 | - | - | bar: NA to NA; NA to -
MA-121 | IACAD | 0% | Waseem Zawaideh | Active | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | 202111_UAE_001 | ITSM | -
MA-119 | MAG - Lab Environment Setup (INFA) | 0% | Stefano El- Khoury | In Progress | 15 | 0 | 0 | 0 | 0 | 0 | 06-19-2023 | 07-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA to NA; NA to -
MA-118 | Dell - Moro - DM CDH to CDP Upgrade | 100% | Mohamed Awad | Completed | 0 | 45 | 0 | 6 | 0 | 0 | 06-06-2023 | 05-09-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | DELL - MORO | PR00000048 | Maaloomatiia | OPP-518715
MA-117 | PoC - G42 CDP Setup | 0% | Stefano El- Khoury | Cancelled | 0 | 0 | 0 | 0 | 0 | 0 | 05-01-2023 | 06-12-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Maaloomatiia | - | bar: NA to NA; NA to -
MA-116 | AD Police - BMC Helix ITSM | 22% | Sagar Petluri | Active | 79 | 23 | 0 | 0 | 0 | 0 | 06-30-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | OPP-477309 | ITSM | -
MA-115 | ADIB - Informatica Support | 50% | Rakesh Rathod | In Progress | 4 | 4 | 1 | 0 | 0 | 0 | - | - | AED 0.00 | AED 0.00 | AED 0.00 | 1530:00 | 123:30 | 1406:30 | AED 0.00 | Based on Project | Based on Staff Hours | 1302:30 | AED 0.00 | Staff Augmentation | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | - | - | PR00000276 | Maaloomatiia | -
MA-114 | DAMAN - Informatica Support | 21% | Rakesh Rathod | In Progress | 11 | 3 | 2 | 0 | 0 | 0 | 01-01-2023 | 01-31-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 60678:00 | 6146:26 | 54531:34 | AED 0.00 | Based on Project | Based on Staff Hours | 54645:38 | AED 0.00 | Staff Augmentation | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | - | - | PR00000444 | Maaloomatiia | -
MA-113 | Ooredoo Qatar - Informatica Support | 0% | Stefano El- Khoury | Completed | 0 | 0 | 1 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Maaloomatiia | - | bar: NA to NA; NA to -
MA-112 | RPA Project Template - Process | 0% | Khaled Mostafa | Junk - Internal | 2 | 0 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | [17 empty] | 202111_UAE_001 | - | - | bar: NA to NA; NA to -
MA-111 | Arab Bank - Cash optimization - Egypt | 96% | Jessica Aoun | Completed | 2 | 47 | 0 | 5 | 0 | 1 | 04-30-2023 | 12-29-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Egypt | - | PR00000082 | Maaloomatiia | OPP-518894
MA-109 | ENOC: TSCO implementation | 0% | Waseem Zawaideh | Active | 1 | 0 | 0 | 0 | 0 | 0 | 05-10-2023 | 09-22-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | OPP-430158 | ITSM | -
MA-108 | MAGNOOS (Internal) | 11% | Stefano El- Khoury | Active | 150 | 19 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | INT | - | - | bar: NA NA to NA NA; NA NA to - -
MA-106 | SAIB - RPA Project | 18% | Khaled Mostafa | Active | 49 | 11 | 1 | 0 | 0 | 0 | 05-15-2023 | 06-17-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | [17 empty] | 202111_UAE_001 | - | - | bar: NA NA to NA NA; NA NA to - -
MA-105 | HCT - Managed Services | 100% | Farah Youssef | Completed | 0 | 49 | 0 | 0 | 0 | 0 | 02-14-2022 | 02-09-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 2431:10 | 1008:58 | 1422:12 | AED 0.00 | Based on Milestone | Fixed Price for Project | 1008:58 | AED 0.00 | DMA | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | HCT - CDA - MAT | PR00000029 | - | -
MA-104 | HCT - Data Science PoC | 0% | Stefano El- Khoury | Cancelled | 6 | 0 | 4 | 0 | 0 | 0 | 05-01-2023 | 06-12-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | Maaloomatiia | -
MA-103 | AJC - Helix ITSM | 0% | Sagar Petluri | Active | 3 | 0 | 0 | 0 | 0 | 0 | 07-31-2023 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | OPP-550795 | ITSM | -
MA-100 | MAG - Data Warehouse | 0% | Stefano El- Khoury | In Progress | 15 | 0 | 1 | 0 | 0 | 0 | 05-01-2023 | 08-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA to NA; NA to -
MA-97 | AD Police - Data Governance | 98% | Jessica Aoun | Completed | 0 | 73 | 0 | 15 | 1 | 0 | 11-30-2022 | 11-18-2024 | AED 0.00 | AED 0.00 | AED 0.00 | 4760:30 | 2795:45 | 1964:45 | AED 0.00 | Based on Milestone | Fixed Price for Project | 2795:45 | AED 0.00 | DMA | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR00000369 | Maaloomatiia | OPP-490772
MA-96 | Omantel EDWH | 72% | Hussein Hammoud | In Progress | 456 | 1246 | 5 | 2 | 26 | 8 | 02-28-2023 | 01-11-2026 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000047 | Maaloomatiia | OPP-518717/OPP-506926
MA-94 | STC pay - Upgrade Services & Two (2) POCs for archiving and ingesting Temenos data | 72% | Jessica Aoun | On Hold | 3 | 8 | 5 | 0 | 0 | 0 | 03-26-2023 | 06-30-2023 | NA | NA | NA | NA | NA | NA | NA | None | Fixed Price for Project | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR000000 | Maaloomatiia | OPP-517222
MA-93 | NBI: Credit Bureau Reports | 22% | Akshara Mannapra | Completed | 7 | 2 | 6 | 0 | 0 | 0 | 03-31-2023 | 07-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Jordan | - | PR000000 | Maaloomatiia | OPP-523986
MA-92 | BAJ: Helix and Discovery | 66% | Sagar Petluri | Active | 5 | 9 | 2 | 0 | 0 | 1 | 09-01-2022 | 05-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | OPP-473232 | ITSM | -
MA-90 | AUB - BMC Helix ITSM Implementation | 58% | Waseem Zawaideh | Active | 7 | 13 | 2 | 0 | 3 | 1 | 11-23-2022 | 08-23-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Bahrain | - | 202111_UAE_001 | ITSM | -
MA-87 | NBF: ITSM (SaaS), Discovery and Client Management | 70% | Akshara Mannapra | Active | 1 | 11 | 2 | 0 | 4 | 1 | 09-30-2021 | 05-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | OPP-336300 | ITSM | -
MA-86 | DIB - Helix ITSM Implementation | 86% | Sagar Petluri | Active | 17 | 131 | 5 | 0 | 3 | 2 | 06-22-2022 | 06-26-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | ITSM | -
MA-85 | SAMACO: ITSM, Discovery, Client Management | 80% | Akshara Mannapra | Active | 4 | 13 | 1 | 0 | 0 | 3 | 02-13-2023 | 05-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | OPP-516752 | ITSM | -
MA-84 | FAB - Archiving project | 0% | Waseem Zawaideh | Active | 5 | 0 | 1 | 0 | 0 | 0 | 09-29-2021 | 04-28-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | ITSM | -
MA-83 | CdM - Control-M Professional Services | 100% | Waseem Zawaideh | Active | 0 | 12 | 1 | 0 | 0 | 0 | 12-31-2021 | 04-28-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Morocco | - | 202111_UAE_001 | ITSM | -
MA-82 | Daman - ITSM Migration | 0% | Waseem Zawaideh | On Hold | 52 | 0 | 0 | 0 | 1 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DSM | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | 202111_UAE_001 | - | -
MA-81 | OO-ISM - Big Data Solution Implementation | 100% | Hussein Hammoud | Completed | 0 | 103 | 3 | 4 | 0 | 0 | 02-15-2023 | 09-26-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000373 | Maaloomatiia | OPP-506986
MA-80 | SAIB - Data Governance | 99% | Stefano El- Khoury | Completed | 0 | 220 | 10 | 0 | 1 | 4 | 12-30-2022 | 02-07-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR00000004 | Maaloomatiia | OPP-415615
MA-79 | AD Ports - Enterprise AI Platform | 86% | Karim Fleifel | In Progress | 43 | 312 | 4 | 5 | 9 | 31 | 12-31-2022 | 01-19-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | PR00000329 | Maaloomatiia | OPP-456493
MA-78 | Leaves | 0% | Stefano El- Khoury | Active | 5 | 0 | 0 | 0 | 0 | 0 | 01-01-2023 | 12-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202111_UAE_001 | Internal MAT | - | bar: NA NA NA to NA NA NA; NA NA NA to - - -
MA-77 | OO-EDP-CR5/Single Rating | 100% | Hussein Hammoud | Completed | 0 | 38 | 0 | 4 | 0 | 1 | 08-17-2022 | 07-28-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000003 | Maaloomatiia | OPP-518504
MA-76 | OO-EDP-CR4/CVM | 95% | Hussein Hammoud | Completed | 1 | 23 | 2 | 4 | 0 | 0 | 08-09-2022 | 12-15-2022 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | Maaloomatiia | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000003 | Maaloomatiia | OPP-518504
MA-75 | DEWA R&D - Data Lake | 100% | Hussein Hammoud | Completed | 0 | 113 | 16 | 0 | 0 | 0 | 08-10-2022 | 08-31-2024 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | PR00000006 | Maaloomatiia | OPP-518482
MA-72 | RTA - Implementation of Enterprise AI Platform | 97% | Jessica Aoun | In Progress | 7 | 345 | 22 | 23 | 2 | 0 | 04-27-2022 | 12-31-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | MAG - Telelogix - Emircom | PR00000064 | Maaloomatiia | OPP-518650
MA-61 | DM- EIA & MDM | 100% | Hussein Hammoud | Completed | 0 | 233 | 5 | 13 | 0 | 2 | 03-08-2022 | 02-28-2025 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | UAE | - | PR00000280 | Maaloomatiia | OPP-359421
MA-60 | Omnix - ERP & PMIS Integration | 0% | Stefano El- Khoury | On Hold | 0 | 0 | 0 | 0 | 0 | 0 | 03-01-2022 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | 202203_UAE_OMNIX_50 | Maaloomatiia | - | bar: NA to NA; NA to -
MA-59 | Arab Bank - Power BI Optimization | 100% | Elias Elwerr | Completed | 0 | 10 | 1 | 0 | 0 | 0 | 03-20-2022 | 03-31-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA | DMA, T&M | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | 202203_JOR_AB_55 | Maaloomatiia | -
MA-55 | Internal | 20% | Stefano El- Khoury | Active | 36 | 9 | 0 | 0 | 0 | 0 | - | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | [17 empty] | PR000000 | Internal MAT | - | bar: NA to NA; NA to -
MA-54 | OO - EDP | 100% | Hussein Hammoud | Completed | 0 | 242 | 0 | 22 | 0 | 3 | 11-21-2021 | 04-30-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Oman | - | PR00000010 | Maaloomatiia | OPP-518504
MA-39 | AXA - Enterprise Analytics Platform | 63% | Maroun Aaraj | On Hold | 166 | 290 | 10 | 6 | 0 | 5 | 12-31-2021 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR000000 | Maaloomatiia | OPP-518412
MA-36 | OO - Data Sanitization | 100% | Hussein Hammoud | Completed | 0 | 152 | 5 | 0 | 0 | 1 | 12-31-2021 | - | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | Staff Augmentation | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | OMAN | - | PR00000030 | Maaloomatiia | OPP-518674
MA-33 | OQ - Big Data Phase 1 | 60% | Elias Elwerr | On Hold | 63 | 95 | 9 | 0 | 3 | 7 | 09-19-2021 | 04-30-2022 | NA | NA | NA | NA | NA | NA | NA | None | Based on Project Hours | NA | NA | Dataiku, ML, DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - | - | 202110_QTR_OQ_NCR_33 | Maaloomatiia | -
MA-22 | CMA - Big Data Services | 71% | Stefano El- Khoury | Delayed | 48 | 123 | 4 | 12 | 1 | 2 | 12-31-2021 | 09-30-2023 | NA | NA | NA | NA | NA | NA | NA | None | Based on Staff Hours | NA | NA | DMA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | KSA | - | PR00000042 | Maaloomatiia | OPP-518689
MA-14 | HCT - Digital Campus (Big Data) | 92% | Dalia El Hajj | Completed | 1 | 26 | 8 | 0 | 1 | 0 | 01-29-2019 | 02-09-2024 | $ 0.00 | $ 0.00 | $ 0.00 | 35136:00 | 685:24 | 34450:36 | $ 6,81,766.00 | Based on Milestone | Based on Staff Hours | 13969:24 | $ 0.00 | DMA | $ 0.00 | $ 0.00 | $ 0.00 | - | - | - | - | - | - | - | - | 0:00 | UAE | - | PR000000 | Maaloomatiia | OPP-518672